## Production scenario for SciFi detector module

At winding centre:
Cast fibre mat
Work load:
1. clean mould (cleaning, applying non-sticking layer, heating)
2. glue fishing lines
3. close casting form
4. mix glue
5. fill glue
6. remove mat from mould (after curing)

Estimated working time per fibre mat: 2 hours for two technicians
Curing time: 2 days

Tools:
1. 2 casting jig/winding centre (to cast two fibre mats at once)
  Price estimate: 5000 Euro/jig
2. 1 water heating circuit (e.g. JULABO MC-4)
  Price estimate: 1646Euro

Costs per fibre mat:
60 Euro for glue

Transversal cut
Polish fibre ends
Work load:
1. Align fibre mat on milling machine
2. cut fibre ends
3. same for second end

Estimated working time per fibre mat: 1 hour for one technician

Tools:
1. 1 Standard milling machine / winding centre
2. 1 2-blade diamond milling head / winding centre
  cost estimate: 1.000 Euro
Glue mirror
Work load:
1. Align fibre mat in gluing jig
2. prepare glue
3. glue mirror
Estimated working time pre fibre mat: 0.5 hours for one technician
Curing time: 1 day
Tools:
1 jig / winding centre
cost estimate: 500 Euro / jig

Total work load for 1 fibre mat:	6hours (winding excluded)

At Module Assembly Centre (MAC)
Longitudinal cut:

Work load:
1. Align fibre mat on milling machine
2. cut fibre mat
Estimated working time per fibre mat: 1 hour for one technician
Tools:
1. Milling machine with long table (~1.5m) / MAC
2. 1 double blade circular mill 'Kreisfräse' / MAC
  cost estimate: ~500Euro
Initially a normal double saw blade has been used. The main problem with this was that the chips are not sufficiently removed and start to melt, resulting in a bad surface and ripping off fibres from the mat.

Glue end-plug & honeycomb on flat side of fibre mat
Work load:
1. prepare jig (cleaning)
2. prepare end-plug (cleaning & grinding)
3. align fibre mat in jig
4. prepare fibre mat (cleaning & grinding)
5. mix glue
6. apply glue and place end-plugs
7. apply glue and place honeycomb panel
8. place vacuum bag and apply vacuum

Estimated working time: 3 hours for two technicians
Curing time: 12 hours

Tools:
  1 template / MAC
1. cost estimate: 15.000-20.000Euro / template
        (OT: 30.000Euro for two template + 33.000Euro for development)
Glue end-plug & honeycomb on pin side of fibre mat
Work load:
1. prepare end-plug (cleaning & grinding)
2. align fibre mat in jig
3. prepare fibre mat (cleaning & grinding)
4. mix glue
5. apply glue and place end-plugs
6. apply glue and place honeycomb panel
7. place vacuum bag and apply vacuum

Estimated working time: 3 hours for two technicians
Curing time: 12 hours

Tools:
  1 template / MAC
1. cost estimate: 5000Euro / template

Wrap module
Work load: Wrap module with light and gas tight envelope
Estimated time: 1 hour for two technicians

Total work load for 1module: 14 hours per module

## Module assembly site:
Remark: assuming Großraumlabor at Heidelberg university

Testing area
Production area
Exhaust hood
(glue mixing)
Cabinet for chemicals
Exhaust hood
(glue mixing)
sink
cabinet
cabinet
Table 1
Table 2
Table 3
Table 4
Table 5
Cabinet
Table 1:	Gluing HC panel on flat fibre mat side
Table 3:	Gluing HC panel on fibre mat side with pins
Table 3:	Gluing sidewalls/wrapping module
Table 5&6:	Tests (dark room???)